## Feuille 1
Task | Action | Priority | Responsible | Deadline | Comment - Avancement, remarques... Jules en bleu Tanguy en vert | Status
Créer un environnement collaboratif | - Créer tout les appli/liens - Template de base pour chaque doc | Medium | Tanguy | 2025-11-30 | Full flexible et en fonction des besoins avec le temps | Ongoing
Créer une identité | - Nom/ logo / - Chart visuel | Low | Les deux |  | Peut se faire dans le temps | To start
Contact | - Ecrire tout les infos des contacts lié à l'expo a Paris - Ajouter liste potentiel interessés | High | Jules |  | Priorité pour ne pas oublier | Done
Etablir règles de collaboration | - Se mettre d'accord sur les prises de decisions - La repartition des rôles - ... | Medium | Les deux |  | Doit être flexible et un sujet toujours ouvert | To start
Créer les bases de notre stratégie |  | Medium | Les deux |  |  | To start
Creer un document clair du montage et démontage |  | Low | Les deux |  |  | To start
Creer un document clair de la partie electronique |  | Low | Jules |  |  | To start
Partager tout les infos financière lié au simulateur | - pièces détachés, location, entretien, si pimpage selon besoin... | Low | Jules |  |  | Ongoing
Ajouter/adapter présentation produit/service |  | Medium | Les deux |  | Remaques draftés après première présentation faite | Ongoing
Checker idées dans Sandbox |  | Low | Les deux |  |  | To start
Trouver tout la doc des ingénieurs sur le simu |  | Low | Jules |  |  | To start
Idée pimper simulateur | - voir le potentiel - adaptation à differents niveaux de coûts | Low | Jules |  |  | To start
Approche Fred |  | Low | Les deux |  |  | Ongoing
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD
|  | TBD |  |  |  | TBD